RECON SENTINEL

MVP Sprint Plan

6-Week Build Plan for AI-Powered External Reconnaissance Platform

March 2026

Incorporates all 27 design amendments from v2.1 addendum

Architecture v2.0 | Schema v1.1 | Addendum v2.1

CONFIDENTIAL

# Table of Contents

# Sprint Overview

This document is the executable build plan for Recon Sentinel MVP. Each week specifies daily tasks, acceptance criteria, dependencies, risk mitigations, and a concrete checkpoint that proves the week's work actually runs. The plan assumes a solo developer working full-time. Tasks are sequenced on the critical path — Week N depends on Week N-1 unless noted otherwise.

## What Exists (Starting Position)

| Artifact | Lines | Status |
| --- | --- | --- |
| PostgreSQL Schema v1.1 | 985 SQL | Locked — 29 tables, 57 indexes, 4 functions |
| SQLAlchemy Models | 844 Python | Locked — matches schema 1:1 |
| Pydantic Schemas | 540 Python | Locked — 47 request/response models |
| FastAPI Routes | 1,440 Python | Locked — 88 endpoints, 15 modules, 2 WebSocket |
| Python Enums | 144 Python | Locked — 18 types mapping to PostgreSQL |
| UI Mockup v5 | 1,715 JSX | Reference — 13 views + P1 features |
| Architecture v2.0 | ~40 pages | Reference — full system design |
| Addendum v2.1 | ~30 pages | Reference — 27 amendments |

## What Will Be Built (6-Week Output)

| Deliverable | Week | Definition of Done |
| --- | --- | --- |
| Runnable Docker Compose (8 containers) | 1 | docker compose up → all services healthy |
| JWT auth + audit + rate limiting | 1 | Register, login, token blacklist, audit log captures 401/403 |
| 3 core agents (subdomain, port, web recon) | 2 | Scan creates findings with MITRE tags + screenshots in DB |
| LangGraph orchestrator + approval gates | 3 | Phase 1 → Gate 1 pause → approve → Phase 2 starts |
| WebSocket real-time + React frontend | 4 | Browser shows live agent progress + findings table |
| Self-correction + re-plan + 6 more agents | 5 | Agent hits WAF → self-corrects → health feed shows event |
| Scope enforcement + hardening + tests | 6 | Full end-to-end scan lifecycle, containerized, deployable |

# Week 1: Infrastructure + Authentication

THEME: Make it boot. Make it secure. Nothing runs without this.

## Daily Breakdown

| Day | Task | Output |
| --- | --- | --- |
| Mon | Docker Compose: PostgreSQL 16, Redis 7, FastAPI (uvicorn), Celery worker, Celery beat, Nginx reverse proxy, Ollama (optional) | docker compose up → 6+ containers running, health checks pass |
| Mon | Docker secrets: JWT signing key mounted at /run/secrets/jwt_secret, DB password as secret, never env vars (Amendment #20) | .gitignored secrets/ directory, Python reads from /run/secrets/ |
| Tue | Alembic init: Generate initial migration from SQLAlchemy models, create all 29 tables + extensions + enums | alembic upgrade head creates full schema |
| Tue | MITRE seed data: Load 30 techniques into mitre_techniques table | SELECT count(*) FROM mitre_techniques = 30 |
| Wed | JWT auth: bcrypt hashing (passlib), python-jose JWT encode/decode, get_current_user dependency, oauth2_scheme | POST /auth/register + /auth/login returns JWT |
| Wed | Token blacklist: Redis-backed revocation, checked on every request, revoke on logout + password change (Amendment #19) | Logout → immediate token rejection on next request |
| Thu | API key fallback: SHA-256 hash validation, X-API-Key header, rate limiting with Redis sliding window — 10 failures/min → 15min lockout (Amendment #22) | Brute-force 11 bad keys → 429 + 15min lockout |
| Thu | Audit middleware: Log ALL methods + ALL statuses including 401/403/429, monthly table partitioning prep (Amendment #21) | Failed login → audit_log row with status=401, ip_address filled |
| Fri | Celery config: Redis broker, JSON serializer, task routing by queue name, result backend, beat schedule | celery worker starts, picks up test task, stores result |
| Fri | Integration test: Register → login → create org → create project → create target → verify audit trail | curl script runs end-to-end, all DB rows verified |

## Week 1 Checkpoint

PASS CRITERIA: docker compose up → all services start → register user → login → create org/project/target via curl → logout → old token rejected → 11 bad API keys → lockout → audit_log has rows for every action including failures.

## Amendments Addressed

- #19 JWT token blacklist + revocation

- #20 SECRET_KEY as Docker secret

- #21 Audit log: all statuses + partitioning

- #22 API key rate limiting

## Risk: Alembic + SQLAlchemy Enum Sync

PostgreSQL enums created by CREATE TYPE don't auto-sync with Alembic autogenerate. Mitigation: use alembic_utils or manually add CREATE TYPE in the first migration before create_all. Test by running upgrade + downgrade + upgrade.

# Week 2: Core Agents

THEME: First scan produces real findings. Prove the agent model works.

## Daily Breakdown

| Day | Task | Output |
| --- | --- | --- |
| Mon | Agent base class: async subprocess execution (asyncio.create_subprocess_exec — NEVER subprocess.run, Amendment #10), progress reporting via Redis pub/sub, scope checking hook | BaseAgent with run(), report_progress(), check_scope() |
| Mon | Finding creation helper: auto-generates fingerprint, sets MITRE tags, calls mitre_finding_counts trigger | create_finding() → finding + mitre_finding_counts updated |
| Tue | Subdomain agent: Wrap Subfinder + crt.sh API + DNS brute. Parse JSON output, create findings with T1593/T1596 tags, create subdomain detail rows | Run against test domain → subdomains table populated |
| Wed | Port/service agent: Wrap Nmap (async, -sT -Pn for non-root) + Naabu for fast pre-scan. Parse XML output, create open_ports rows with service detection | Run against test host → open_ports with service versions |
| Thu | Web recon agent: Wrap httpx (probe live hosts) + GoWitness (screenshots) + Wappalyzer (tech detection). Store screenshots to filesystem, create screenshot rows | Run against subdomains → screenshots stored, tech_detected filled |
| Thu | Install recon tools in worker container: Subfinder, Nmap, Naabu, httpx, GoWitness in Dockerfile, verify each runs | docker exec worker subfinder -version → OK for all tools |
| Fri | Celery task wiring: Each agent registers as a Celery task, dispatched by scan_id, reports progress to Redis, creates findings on completion | Launch scan → 3 tasks dispatched → findings appear in DB |
| Fri | API integration: GET /findings returns results, GET /findings/stats returns severity counts, MITRE heatmap populated | curl /api/v1/findings?scan_id=... returns JSON findings with MITRE tags |

## Week 2 Checkpoint

PASS CRITERIA: POST /scans → 3 agents run as Celery tasks → subdomains, open ports, screenshots stored → GET /findings returns results with MITRE technique IDs → GET /mitre/heatmap returns non-empty data.

## Risk: Tool Installation in Docker

Go-based tools (Subfinder, httpx, Naabu) need Go compiler at build time or pre-built binaries. Mitigation: use official release binaries from GitHub Releases, download in Dockerfile RUN step, verify checksums. GoWitness needs Chrome — install chromium-browser in the worker-browser container profile (Amendment #18).

# Week 3: Orchestration + Approval Gates

THEME: The AI orchestrator comes alive. Human-in-the-loop gates work.

## Daily Breakdown

| Day | Task | Output |
| --- | --- | --- |
| Mon | LangGraph state machine: Define ReconState (phase, agents, findings_summary, gate_decisions, replan_count, replan_cost_usd, checkpoint). Implement phase transition nodes | State machine compiles, transitions passive → gate_1 → active |
| Mon | Checkpoint persistence: Serialize LangGraph state to scans.langgraph_checkpoint (JSONB). Load on resume | Pause scan → kill worker → restart → scan resumes from checkpoint |
| Tue | LiteLLM integration: Configure model routing (Haiku for planning, Sonnet for analysis), prompt caching, usage logging to llm_usage_log on every call including fallback | LLM call → llm_usage_log row with model, tokens, cost |
| Tue | LLM fallback: LiteLLM fallback chain with task allowlist — block replan/mitre/scope/gate tasks from local models (Amendments #7, #25) | Claude down → chat falls back to Ollama → replan raises LLMUnavailableError |
| Wed | Gate 1 generation: After passive phase completes, Haiku summarizes findings + recommends active scan scope → creates approval_gate row → scan status changes to paused | Passive agents complete → approval_gate row appears with ai_summary |
| Wed | Gate decision API: POST /scans/{id}/gates/1/decide → validate decision → update gate → signal LangGraph to resume → Phase 2 agents dispatch | Approve gate → active agents start running within 5 seconds |
| Thu | WebSocket manager: Redis pub/sub subscriber → ConnectionManager → broadcast events to /ws/scan/{id}. Events: agent.status, agent.finding, scan.gate, scan.phase | Connect WS → launch scan → receive live agent.status events |
| Thu | Re-plan circuit breaker: max_replan_iterations=3, max_replan_cost_usd=$0.50, dedup set for oscillation detection (Amendments #16, #24) | Force 4 replans → 4th rejected with 'limit reached' log |
| Fri | Monthly budget check: Pre-call budget validation against configurable cap, 80% warning, 100% pause (Amendment #26) | Set budget=$1 → run 5 scans → 5th scan pauses with budget_exceeded |
| Fri | Full pipeline test: Scan → passive agents → Gate 1 pause → approve → active agents → Gate 2 pause → approve → vuln agents → complete | End-to-end 3-phase scan completes with 2 gate approvals |

## Week 3 Checkpoint

PASS CRITERIA: Launch scan → passive agents run → Gate 1 fires with AI summary → WebSocket pushes scan.gate event → approve via API → active agents start → Gate 2 → approve → scan completes. LLM costs logged. Budget cap enforced. Re-plan limited to 3 iterations and $0.50.

## Risk: LangGraph Checkpoint Serialization

HIGHEST RISK WEEK. LangGraph checkpoint serialization to PostgreSQL JSONB is the least-proven piece of the stack. Fallback: if LangGraph fights checkpoint persistence, replace with a simpler Redis-backed state machine that stores phase + agent_list + gate_status as a JSON blob. This loses LangGraph's graph-level replay but preserves all functional behavior. Migrate to full LangGraph checkpointing post-MVP.

# Week 4: Frontend MVP

THEME: A human can use it. Browser replaces curl.

## Daily Breakdown

| Day | Task | Output |
| --- | --- | --- |
| Mon | Next.js scaffold: Tailwind CSS (dark mode), project structure, auth context (JWT storage in memory, refresh via HttpOnly cookie), SWR for data fetching | npm run dev → blank app with login page |
| Mon | Auth pages: Login, register, logout. Token refresh. Protected route wrapper | Login → redirect to dashboard → refresh persists session |
| Tue | WebSocket hook: useWebSocket(scanId) — auto-reconnect, event dispatch to React state, connection status indicator | Connect to /ws/scan/{id} → receive events in React state |
| Tue | Dashboard view: Stat cards (findings by severity, subdomains, ports, credentials), agent status grid with health indicators | Dashboard shows real scan data from API |
| Wed | Agent orchestration view: Agent cards with real-time progress bars, ETA, current tool, last log line — all via WebSocket | Watch agents run in real time, progress bars animate |
| Wed | Approval gate banner: When scan.gate event arrives, show banner with AI summary + approve/customize/skip buttons | Gate fires → banner appears → click approve → agents resume |
| Thu | Findings view: Table with severity filter, finding type filter, search box, pagination. Click finding → detail panel | Filter by critical → see only critical findings |
| Thu | Findings bulk actions: Checkboxes, select all, mark false positive, add tag (Amendment P1) | Select 5 findings → mark all false positive → DB updated |
| Fri | Scan launch flow: Target input (URL/domain/IP/CIDR), profile selector, scope review panel, launch button | Enter target → select Full profile → launch → redirect to orchestration view |
| Fri | Integration test: Full browser flow — login → create target → launch scan → watch agents → approve gate → view findings | Screen recording of complete flow |

## Week 4 Checkpoint

PASS CRITERIA: Open browser → login → create target → launch scan → watch live agent progress → approval gate banner appears → approve → agents resume → findings table populated → filter by severity works → bulk mark false positive works.

## Risk: WebSocket Reconnection

Browser tab sleep, network interruption, or server restart drops the WebSocket. Mitigation: useWebSocket hook implements exponential backoff reconnection (1s, 2s, 4s, max 30s). On reconnect, fetch current scan state via REST to sync, then resume WS streaming.

# Week 5: Intelligence Layer

THEME: The AI becomes adaptive. Self-correction and re-planning prove the differentiator.

## Daily Breakdown

| Day | Task | Output |
| --- | --- | --- |
| Mon | Self-correction engine: Base class with sense() → analyze() → correct() → report() loop. Retry counter (max 3), escalate_user on exhaustion | BaseSelfCorrector with hook points for each agent |
| Mon | Pattern 1 — Custom 404: Detect >80% same content-length in Dir/File agent → re-run ffuf with -fs {size} | Run against custom-404 test server → auto-corrects → finds real dirs |
| Tue | Pattern 2 — WAF blocking: Detect >95% responses 403 → reduce rate + rotate user-agent → retry | Run against WAF-protected target → detects 403 pattern → adjusts |
| Tue | Pattern 3 — DNS wildcard: Random subdomain resolves to same IP → filter wildcard IP from results | Run against wildcard domain → filters noise → real subdomains remain |
| Wed | Health event pipeline: Create health_event rows (anomaly → correction → success/escalation) → broadcast via WebSocket → render in Agent Health Feed UI | Health feed shows timeline: anomaly detected → self-corrected → success |
| Wed | Re-plan node: Haiku analyzes new findings after Gate 2, suggests ADD/SKIP/MODIFY agents, with circuit breaker + cost guard + dedup (Amendments #6, #16, #24) | Gate 2 approved → re-plan adds JS analysis agent → it runs |
| Thu | 6 more agents: Credential leak (HIBP API), Threat intel (Shodan API), OSINT (theHarvester), Email security (SPF/DKIM), Dir/File (ffuf), SSL/TLS (sslyze) | Each agent produces findings with correct MITRE tags |
| Thu | Error classification: Proxy vs plugin vs API vs target failure distinction in circuit breaker (Amendment #17) | Kill proxy → agent timeout → classified as proxy_error, not plugin_error |
| Fri | MITRE heatmap view: Render technique grid with color-coded cells from mitre_finding_counts, drill-down on click | Heatmap shows T1190 in red (5 critical findings), T1593 in yellow |
| Fri | Recon flow view: Three-phase visual timeline with approval gates, LLM cost per phase, agent status within each phase | Visual shows Phase 1 complete, Gate 1 approved, Phase 2 running |

## Week 5 Checkpoint

PASS CRITERIA: Agent encounters WAF 403s → self-corrects (reduce rate) → health feed shows anomaly + correction → re-plan suggests new agent after Gate 2 → new agent runs → MITRE heatmap renders with real data → error classification distinguishes proxy failure from plugin failure.

## Risk: External API Rate Limits

Shodan, HIBP, and VirusTotal have strict rate limits on free tiers. Mitigation: implement API key verification on first use (POST /settings/api-keys/{id}/verify), show warnings in UI when free tier detected, and use the API exhaustion pause/resume mechanism (Amendment #8) with Redis distributed lock (Amendment #27).

# Week 6: Hardening + Ship

THEME: Lock it down. Test everything. Deploy.

## Daily Breakdown

| Day | Task | Output |
| --- | --- | --- |
| Mon | Scope enforcement: Wire is_in_scope() into agent base class pre-execution check. Create scope_violations on blocked requests. Scope control UI view | Agent tries out-of-scope target → blocked → violation logged → visible in UI |
| Mon | Plugin iptables scope enforcement: Generate iptables ruleset from scope_definitions, inject into plugin containers (Amendment #23) | Plugin container → iptables -L shows only in-scope IPs allowed |
| Tue | Dual container profiles: worker-tools (strict) and worker-browser (Chrome-capable). Separate Celery queues with task routing (Amendment #18) | web_recon task routes to worker-browser, port_scan to worker-tools |
| Tue | Container hardening: Non-root, cap_drop ALL, seccomp profile for browser, read-only rootfs, tmpfs limits | docker exec worker whoami → nonroot, capsh shows only NET_RAW |
| Wed | Report generation: Celery task uses Sonnet to generate executive summary + full report → PDF/DOCX via WeasyPrint/python-docx → file stored → downloadable via API | POST /reports → async generation → GET /reports/{id}/download returns PDF |
| Wed | AI Copilot Chat (basic): Session creation, message send → Sonnet with scan context → streaming response via /ws/chat/{session_id}. /findings and /summarize slash commands | Type /summarize → AI returns scan summary referencing actual findings |
| Thu | Remaining UI views: Scope control, reports (generate + list + download), settings (API keys + scan engines + LLM usage) | All P0 views functional with real data |
| Thu | API resume distributed lock: Redis SETNX for rate-limit resume coordination (Amendment #27) | Two workers detect rate-limit expiry → only one resumes agents |
| Fri | End-to-end integration test: Full scan lifecycle with all 9 agents, both gates, self-correction trigger, scope violation, report generation | Test script runs complete lifecycle, all assertions pass |
| Fri | Deployment docs: README with setup instructions, .env.example (no secrets!), docker-compose.prod.yml with healthchecks, backup script for PostgreSQL | Fresh machine → clone repo → follow README → working deployment |

## Week 6 Checkpoint

PASS CRITERIA: Complete scan lifecycle: launch → 9 agents across 3 phases → 2 gate approvals → self-correction fires → scope violation blocked and logged → report generated → chat returns scan-aware summary → all running in hardened containers with iptables scope enforcement → deployable on fresh machine via README.

## Risk: Time Pressure on Hardening

Week 6 is the most overloaded — hardening, reports, chat, and testing all compete. Mitigation: if time is tight, defer AI Copilot Chat to Week 7 (it's impressive but not on the critical scan path). Reports and scope enforcement are non-negotiable for a security product.

# Risk Register

| Risk | Likelihood | Impact | Week | Mitigation |
| --- | --- | --- | --- | --- |
| LangGraph checkpoint fails with PostgreSQL JSONB | MEDIUM | HIGH | 3 | Fallback: Redis-backed state machine (JSON blob) with same API surface |
| Alembic enum sync issues | HIGH | LOW | 1 | Manual CREATE TYPE in first migration, test upgrade/downgrade/upgrade |
| Go tool binary compatibility in Docker | MEDIUM | MEDIUM | 2 | Pin exact release versions, verify checksums, test in CI |
| Chromium sandbox in Docker | MEDIUM | MEDIUM | 2,6 | worker-browser profile with SYS_ADMIN + seccomp allowlist (Amendment #18) |
| External API rate limits on free tiers | HIGH | MEDIUM | 5 | API key verification, free tier warnings, pause/resume mechanism |
| LLM hallucination in re-plan decisions | MEDIUM | HIGH | 5 | Circuit breaker (3 iterations, $0.50), dedup set, fallback task allowlist |
| Week 6 overload (too many deliverables) | HIGH | MEDIUM | 6 | Defer Copilot Chat to Week 7 if needed, scope enforcement + reports are non-negotiable |
| WebSocket reconnection after server restart | MEDIUM | LOW | 3,4 | Exponential backoff reconnection + REST state sync on reconnect |
| MITRE trigger deadlock under high concurrency | LOW | MEDIUM | 2 | ON CONFLICT DO UPDATE + advisory_lock if contention observed |
| Surprise LLM costs from re-plan loops | MEDIUM | HIGH | 3 | Cost guard ($0.50/scan), monthly budget cap, auto-pause (Amendments #24, #26) |

# Post-MVP Backlog (Weeks 7+)

These features are designed and documented but not on the MVP critical path. Ordered by value:

| Priority | Feature | Effort | Depends On |
| --- | --- | --- | --- |
| P1 | Notification channels (Discord, Slack, Telegram, Email, Webhook) | 2 days | Core MVP |
| P1 | Scan history + diff comparison view | 2 days | Multiple completed scans |
| P1 | Scan engine YAML editor + custom profiles | 1 day | Settings UI |
| P1 | Command palette (Ctrl+K) + backend /search endpoint | 1 day | pg_trgm indexes (already created) |
| P1 | Cost dashboard (LLM spend per scan/org + monthly projection) | 1 day | llm_usage_log populated |
| P1 | RLS policies (multi-tenant isolation) | 1 day | JWT auth (Week 1) |
| P1 | Credential KMS/Vault integration + key rotation | 2 days | Encryption architecture |
| P1 | Proxy chain support (SOCKS5/HTTP config per scan) | 1 day | Agent base class |
| P1 | Cloud agent dangling DNS expansion (Azure/AWS/GCP) | 1 day | Cloud agent |
| P1 | HackerOne/Bugcrowd scope import | 1 day | Scope control UI |
| P2 | Plugin system runtime + marketplace | 5+ days | Container profiles, iptables enforcement |
| P2 | OpenTelemetry + Prometheus /metrics | 2 days | Core MVP |
| P2 | Mobile responsiveness | 3 days | Frontend MVP |
| P2 | Findings versioning + soft-delete | 1 day | Findings pipeline |
| P2 | Onboarding wizard | 2 days | Frontend MVP |

# Amendment Traceability Matrix

Every amendment from the v2.1 addendum is mapped to a specific sprint week and task:

| # | Amendment | Sprint Week | Status |
| --- | --- | --- | --- |
| 1 | JWT authentication | Week 1 (Wed) | Scheduled |
| 2 | Audit log middleware | Week 1 (Thu) | Scheduled |
| 3 | Credential KMS/Vault | Post-MVP | Backlog |
| 4 | Row-level security | Post-MVP | Backlog |
| 5 | Container capability dropping | Week 6 (Tue) | Scheduled |
| 6 | Re-plan adaptive loop | Week 5 (Wed) | Scheduled |
| 7 | LLM fallback policy | Week 3 (Tue) | Scheduled |
| 8 | API exhaustion pause/resume | Week 5 (risk mitigation) | Scheduled |
| 9 | Command palette backend | Post-MVP | Backlog |
| 10 | Async subprocess constraint | Week 2 (Mon) | Scheduled |
| 11 | OpenTelemetry + Prometheus | Post-MVP | Backlog |
| 12 | Cost dashboard | Post-MVP | Backlog |
| 13 | Findings soft-delete | Post-MVP | Backlog |
| 14 | Cloud agent dangling DNS | Post-MVP | Backlog |
| 15 | Proxy chain support | Post-MVP | Backlog |
| 16 | Re-plan circuit breaker + dedup | Week 3 (Thu) | Scheduled |
| 17 | Error classification: proxy vs plugin | Week 5 (Thu) | Scheduled |
| 18 | Dual container profiles | Week 6 (Tue) | Scheduled |
| 19 | JWT token blacklist | Week 1 (Wed) | Scheduled |
| 20 | SECRET_KEY Docker secret | Week 1 (Mon) | Scheduled |
| 21 | Audit log: all statuses + partitioning | Week 1 (Thu) | Scheduled |
| 22 | API key rate limiting | Week 1 (Thu) | Scheduled |
| 23 | Plugin iptables scope enforcement | Week 6 (Mon) | Scheduled |
| 24 | Re-plan cost guard ($0.50) | Week 3 (Thu) | Scheduled |
| 25 | LLM fallback task allowlist | Week 3 (Tue) | Scheduled |
| 26 | Monthly LLM budget cap | Week 3 (Fri) | Scheduled |
| 27 | API resume distributed lock | Week 6 (Thu) | Scheduled |